## Slide 1: Ped-bc blood donation portal
PHILIPPINE CHILDREN’S MEDICAL CENTER
BLOOD DONATION INFORMATION SYSTEM

## Slide 2: Project Overview
Purpose
  To assist the Medical Blood Donation (MBD) Team in managing blood donations efficiently.
  To enable donors to register, schedule, and track their blood donations.
  To educate and spread awareness about voluntary blood donation.
  To provide real-time donation tracking, event booking, and emergency blood request features.
  To streamline coordination between donors, agencies, and the MBD team.

## Slide 3: End-Users
Roles
  Donors – Agency employees/personnel who donate blood.
  Agency Account Managers – Manage blood drive hosting accounts.
  Agency Coordinators – Organize donation events and manage donor records.
  MBD Team – Oversees blood drive requests, approvals, and notifications.

## Slide 4: Scope & functionalities
PedBC Blood Donation Portal

## Slide 5: Project scope
Develop a web and mobile application for blood donation management.
Implement role-based access for different users (Donors, Agency Managers, Coordinators, MBD Team).
Provide real-time notifications and a centralized dashboard for monitoring donations.
Support event booking, emergency blood requests, and donor history tracking.
Enable content management for educational materials and announcements.

## Slide 6: Key functionalities by role
PedBC Blood Donation Portal

## Slide 7: For donors
Register as a blood donor.
Schedule and manage donation appointments.
Request emergency blood when needed.
Receive notifications and reminders for next eligibility.

## Slide 8: For agency account managers
Request to manage or host a blood drive.
Approve or reject coordinator registration requests.

## Slide 9: For agency coordinators
Create, edit, and delete blood drive events.
Manage donor lists, donation history, and blood type filtering.
Post announcements for donors.

## Slide 10: For MBD TEAM
Manage blood drive hosting requests from agencies.
Monitor donor history and approve/reject donation events.
Handle blood requests and send notifications to all users.

## Slide 11: Project Timeline (Gantt Chart)
PedBC Blood Donation Portal

## Slide 12: Timeline overview
The timeline will be broken down into phases for development, testing, and deployment.
Each phase will be tied to specific tasks and milestones.

## Slide 13: Phases and Key Milestones
PedBC Blood Donation Portal

## Slide 14: SPRINT 1 - Requirements Gathering & Design (2 Weeks)
Gather data from the end users.
Finalize user roles, functional and technical requirements.
Design Entity Relationship Diagram (ERD) and wireframes.

## Slide 15: SPRINT 1 – milestone & backlogs
MILESTONE
Finalized user roles & initial project requirements
Core ERD and database schema for MVP established.
Initial wireframes for Agency & Donors for approval of the end-users.
BACKLOGS
ERD for Content Management Feature (Not yet finalized).
Wireframes for Account Manager & MBD (Still in progress).

## Slide 16: SPRINT 2 - Frontend and Backend Development (6 Weeks)
Develop user interfaces using ReactJS. (Clickable Prototypes)
Develop the API endpoint with Node.js (Express) and Sequelize.
Implement authentication and authorization with JWT and PassportJS.

## Slide 17: SPRINT 2 – milestone & backlogs
MILESTONE
API endpoints developed using Node.js (Express) and Sequelize.
Authentication and authorization implemented with JWT and PassportJS
Admin UI developed for RBAC (Role-Based Access Control).
CRUD operations implemented for users, roles, and menus.

## Slide 18
Backlogs (Pending/In Progress Work).
Complete UI development for other user roles (Only Admin UI is done)
Develop and integrate more frontend features (Clickable prototypes for all roles)
Enhance API functionalities beyond CRUD (validations & restrictions)
Optimize UI and UX (Enhance responsiveness, accessibility, and user experience)

## Slide 19: SPRINT 3 - Testing & Bug Fixing (1 Week)
Perform unit and integration testing.
Conduct usability testing and bug fixing.

## Slide 20: SPRINT 4 - Deployment & Handover (1 Week)
Deploy the application to the server or cloud-based hosting.
Provide documentation and training materials for the end-users.

## Slide 21: Technical Methodology & Security
PedBC Blood Donation Portal

## Slide 22: Development Methodology: Agile Approach
Sprint-based development with evolving requirements.
Continuous collaboration with end-users for feedback and adjustments.
Iterative releases to ensure core functionalities are delivered early.

## Slide 23: Tech Stack & Tools
Frontend: React Native Web, NativeWind, Expo, Tailwind CSS
Backend: Node.js (Express), Sequelize (ORM), MySQL
Authentication & Security: JWT, PassportJS, RBAC
Database: MySQL
Hosting: (TBD - On-premise or Cloud)
Collaboration & Documentation: ClickUp, Google Sheets

## Slide 24: Security Measures
Authentication & Authorization
JWT-based authentication for API security.
PassportJS for secure authentication flow.
Role-Based Access Control (RBAC) to restrict user permissions.
Data Protection & Encryption
Password hashing before storing user credentials.
SSL encryption for secure data transmission (TBD).

## Slide 25: Security Measures
Access Control & Monitoring
API access restrictions based on user roles.
Security logging & monitoring (TBD).
Backup & Recovery Plan
Regular database backups.

## Slide 26: Infrastructure as Code (IaC) & Hosting
PedBC Blood Donation Portal

## Slide 27: IaC & Hosting
✅ Hosting Options (TBD)
  On-premise: Internal servers within the agency.
  Cloud-based: Vercel or Firebase Hosting.
  Docker for environment consistency.
✅ Scalability & Performance
API Load Balancing & Database Optimization.

## Slide 28: Deliverables
PedBC Blood Donation Portal

## Slide 29: Completed Deliverables (Development Stage - 4 Weeks Progress)
BACK_END
API Endpoints:
Core API structure is implemented..
BACK_END
Authentication:
JWT authentication and PassportJS integration are completed.

## Slide 30: Completed Deliverables (Development Stage - 4 Weeks Progress)
BACK END
RBAC (Role-Based Access Control):
Initial setup for user roles and access control is implemented.
Database & Architecture:
ERD & Database Schema:
Designed and implemented for MVP (Minimum Viable Product).

## Slide 31: Completed Deliverables (Development Stage - 4 Weeks Progress)
Database & Architecture:
CRUD Operations::
Implemented for users, roles, and menus (Admin role UI).
Frontend Progress:
Admin Panel UI:
Basic UI for admin role in RBAC is designed.

## Slide 32: User-defined landing page
Home:
Overview of the Pediatric Blood Center and its mission.
Why Donate:
Educational content about pediatric blood donation.
Donate Blood:
A page for users to learn how to donate and a form to register.
Upcoming Events:
A calendar or list of upcoming blood donation drives.
Success Stories:
Testimonials and stories from families who have benefited from blood donations.
Contact Us:
Address, phone number, and email for inquiries.